## Folha1
Changes applied in release 2.0.1		The change requests are maintained in the ESPD-EDM Github Issue space: https://github.com/ESPD/ESPD-EDM/issues

Issue #ID	Issue Name	Status	Description	Solved in Release	Comments	Impacts	Solution	NEW BUSINESS RULES (SPECIALLY RELEVANT FOR THE BIZDOC)	Mapping between V1.0.2 and V2.0.0	Mapping between V2.0.0 and V2.0.0
133	Unused CodeLists	CLOSED	ActivityType, AmountTypeCode and ContractType code lists seem not be used in any case for the ESPD-EDM 2.0.0.	2.0.1			In version 2.0.1 the ActivityType, AmountTypeCode and ContractType Code Lists have been removed, as they're not used. ContractType is covered by the CodeList "ProcedureType".
132	cac:TenderingCriterionResponse/cac:ResponseValue cannot be mandatory	CLOSED	The current structure for the response allows responding values inside the cac:ResponseValue element or in other elements of the cac:TenderingCriterionResponse, like cac:TenderingCriterionResponse/cac:ApplicablePeriod and cac:TenderingCriterionResponse/cac:EvidenceSupplied. / Therefore the cardinality of the cac:TenderingCriterionResponse/cac:ResponseValue should be 0..* (although in most cases only one value is expected there are some cases where a collection of values must be provided, e.g. a list of Lots IDs, see documentation and examples on Lots).	2.0.1		1. Documentation	This will be corrected in the documentation of the version 2.0.1. Beware that the UBL Schema allows for cardinality 0..*. / Nonetheless this has been subject of discussion with UBL-2.2 (i.e. shouldn't the Period and Evidence be specified as elements of the ResponseValue, instead of elements of the cac:Tendering CriterionResponse, even worse: what is the true semantics of the qualifier "Applicable" in the case of Period) values and was decided to postpone a better design for future versions of UBL.	Cardinality of cac:TenderingCriterionResponse/cac:ResponseValue modified to be 0..n
131	Cardinality of cac:Evidence/cbc:ID should be mandatory	CLOSED	The "/QualificationApplicationResponse/cac:Evidence/cbc:ID" should have a cardinality of 1..1 (currently 0..1). / Reason: If there is an evidence used in the ESPD response, it should be always connected to a criterion and criterion response through a cross reference to the class /QualificationApplicationResponse/cac:TenderingCriterionResponse". / (similar relationsship occurs between "TenderingCriterionResponse" and "cac:TenderingCriterion")	2.0.1		1. Documentation / 2. Business Rules / 3. BizDoc	A Schematron rule has been added to control the cardinality of this element / The documentation has been modified.	Cardinality of the Evidence ID must be 1..1
130	Criteria Taxonomies need to be reviewed	CLOSED	Both the drawings in the documentation as well as the definitions and uuids in the spread-sheets contained in the distribution package need to be reviewed, as some errors have been detected.	2.0.1		1. Documentation / 2. Spreadsheets in folder cl, editorial minor changes	UUDIS in documentation (v.2.0.1) have been reviewed / UUIDs, names and descriptions in files ESPD-REGULATED-CriteriaTaxonomy-V02.00.01 and ESPD-SELFCONTAINED-CriteriaTaxonomy-V02.00.01.xlsx do match now the ones in ESPD-Data_Structures-REGULATED-V02.00.01 and ESPD-Data_Structures-SELFCONTAINED-V02.00.01 spreadsheet books.
128	Unused codelists	CLOSED	The following codelists, distributed in version 2.0.0, are not actually used: / 1- ActivityTypeCode / 2- AmountTypeCode / 3- ContractType (instead the ProjectType codelist, maintained by the Publications Office, is used).	2.0.1		1. CodeList spread-sheets book / 2. Conversions between V 1.0.2 and V2.0.0.	Same as Issue #133		Need to control Code conversions
127	Incorrect requirement about Lots related to ESPD-EDM-2.0.0 REGULATED	CLOSED	The documentation about ESPD-EDM-2.0.0 contains the following requirement: / REQUIREMENT | At least one Lot must be always instantiated in the Regulated ESPD XML document. If the procurement procedure is not divided into Lots the only lot present in the Regulated ESPD XML document represents the procedure, and its Identifier value must be '0'. / It should read: / REQUIREMENT / One Lot must be always instantiated in the Regulated ESPD XML document. It only expects one Lot representing the procurement procedure. / The REGULATED version of the ESPD cannot be used for procurement procedures divided into Lots (for procedures divided into Lots use the SELF-CONTAINED version).	2.0.1		1. BizDoc / 2. ESPD-EDM-2.0.1 DOCUMENTATION	The documentation (in version 2.0.1) reads now: / One Lot must be always instantiated in the REGULATED ESPD XML document, and its identifier value should be '0'. The REGULATED version of the ESPD cannot be used for procurement procedures divided into Lots. / For procedures divided into Lots use the SELF-CONTAINED version.	One Lot must be always instantiated in the Regulated ESPD XML document. It only expects one Lot representing the procurement procedure. / The REGULATED version of the ESPD cannot be used for procurement procedures divided into Lots (for procedures divided into Lots use the SELF-CONTAINED version).
123	Subgroups of Abilities requirements with identical @UUID	CLOSED	In file ESPD-Data_Structures-SELFCONTAINED-V02.00.01 requirement group in data structures SC-Abilities_2_Checks and SC-Abilities_3 have identical UUIDs but the structures are different.	2.0.1		Data Structures	Corrected in release ESPD-EDM v.2.0.1: / SC-Abilities_2_Checks --> Group #ID 9026e403-3eb6-4705-a9e9-e21a1efc867d added inside the requirement group #ID 10822ddd-9ba6-42d5-9339-de0845aeafc9 / SC-Abilities_3 --> Group #ID 9026e403-3eb6-4705-a9e9-e21a1efc867d added inside the requirement group #ID 7f7949a8-dbe6-496c-a9f6-6f05b8648bad
122	Subgroups of requirements with the same ID	CLOSED	In ESPD-Data_Structures-SELFCONTAINED-V02.00.00 the subgroups of requirements SC-General_Turnover, SC-Specific_Turnover, SC-General_Average_Turnover, SC-Specific_Average_Turnover have the same Element UUID 5ca58d66-3ef1-4145-957c-45d5b18a837f, but the structures are different (hence they are separated in different tabs of the spread-sheets book).	2.0.1		Data Structures	The new ESPD-EDM release, version 2.0.1 has corrected this. The new #UUIDs are now: / SC-General_Turnover --> 5ca58d66-3ef1-4145-957c-45d5b18a837f / SC-Specific_Turnover --> 19a68e37-d307-4a28-9061-c22cd767be58 / SC-General_Average_Turnover --> 53882893-f4a8-40ae-99dc-cad7b0748790 / SC-Specific_Average_Turnover --> 6cff132b-8d15-4f79-ae37-2f9295432381
117	Evidence Supplied / Evidence Identifier in ESPD Data Structures	CLOSED	For each criteria there should be a possibility to indicate an evidence through an evidence identifier in order to support the once only principle. If not available, EOs have to re-enter their prequalification information into the ESPD since they are managed in external documents. At least for the following criteria they should be added in order to link to documents available in the German prequalification database: / Breaching of obligations in the fields of social law / Breaching of obligations in the fields of labour law / Guilty of grave professional misconduct / Agreements with other economic operators aimed at distorting competition / Early termination, damages or other comparable sanctions / General yearly turnover / Specific yearly turnover / Average yearly turnover / Specific yearly turnover / Number of managerial staff / Average annual manpower	2.0.1		1) Does not impact on the Data Model. / 2) Impacts on the Data Structures. OBLIGES TO HAVE THE GROUP #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d with cardinality 1 / 3) Impacts on the documentation: all the images on the asciidoc about data structures have to been changed.	All Data Structures in ESPD-Regulated and ESPD-SELFCONTAINED Excels have been reviewed and modified. The images in the documentation too. / The change request can be summed up as follows: the user should be able to associate one or more evidence to any criterion. The followin data structures have been vary now from version 1.0: / REGULATED: / * EG-Convictions -> NO CHANGES! / * EG-Contributions -> NO CHANGES! / * EG-Environ-Social-Labour_Law -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * EG-Business -> NO CHANGES! / * EG-Misconduct -> Group -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * EG-Conflict_of_interest -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * EG-Early_termination -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * EG-Misinterpretation -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * EG-Purely_national -> NO CHANGES! / * SC-Suitability -> NO CHANGES! / * SC-Yearly_Turnovers -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * SC-Average_Turnovers -> NO CHANGES! / * SC-Setup_of_economic_operator -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * SC-Financial_ratios -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * SC-Professional_risk_insurance -> NO CHANGES! / * SC-Other_economic_or_financial -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * SC-References -> NO CHANGES! / * SC-Abilities_1 -> NO CHANGES! / * SC-Abilities_2_checks -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * SC-Abilities_3 -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * SC-Subcontracting_proportion -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * SC-Samples_certificates -> NO CHANGES! / * SC-Quality_assurance -> In this case the Subgroup #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d has been extracted from the / * SC-Quality_assurance -> In this case the Subgroup #UUID 4887c3d7-05fc-4e3e-b066-f338910f0c4c and has been added at the end of the criterion data structure / * OTHER-EO-SHELTERED -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * OTHER-EO-PQS -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * OTHER-EO-GROUPS -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * OTHER-EO-Lots -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * OTHER-EO-Contributions -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * OTHER-EO-NOT_RELIED_ON-ENTITIES -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / SELF-CONTAINED: / * EG-Convictions -> NO CHANGES! / * EG-Contributions -> NO CHANGES! / * EG-Business -> NO CHANGES! / * EG-Misconduct -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * EG-Conflict_of_interest -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * EG-Early_termination -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * EG-Misinterpretation -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * EG-Purely_national -> NO CHANGES! / * SC-Suitability -> NO CHANGES! / * SC-General_Turnover -> Subgroup #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added inside the the requirement group #UUID 5ca58d66-3ef1-4145-957c-45d5b18a837f / * SC-Specific_Turnover -> Subgroup #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added inside the the requirement group #UUID 19a68e37-d307-4a28-9061-c22cd767be58 / * SC-General_Average_Turnover -> Subgroup #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added inside the the requirement group #UUID 53882893-f4a8-40ae-99dc-cad7b0748790 / * SC-Specific_Average_Turnover -> Subgroup #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added inside the the requirement group #UUID 6cff132b-8d15-4f79-ae37-2f9295432381 / * SC-Specific_Average_Turnover -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * SC-Financial_ratios -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * SC-Other_economic_or_financial -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added inside the requirement group #UUID 4ddccd16-91e4-4b72-ae0f-78f2f1ab9490 / * SC-Abilities_2_Checks -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added inside the requirement group #UUID 10822ddd-9ba6-42d5-9339-de0845aeafc9 / * SC-Abilities_3 -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added inside the requirement group #UUID 7f7949a8-dbe6-496c-a9f6-6f05b8648bad / * SC-Subcontracting_proportion -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * SC-Samples_certificates -> NO CHANGES! / * SC-Quality_assurance -> In this case the Subgroup #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d has been extracted from the Subgroup #UUID 4887c3d7-05fc-4e3e-b066-f338910f0c4c and has been added at the end of the requirement_group #UUID 612d99eb-ea3b-4275-ac06-0db05e039c8c / * OTHER-EO-SHELTERED -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * OTHER-EO-PQS -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * OTHER-EO-GROUPS -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * OTHER-EO-Lots -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * OTHER-EO-Contributions -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * OTHER-EO-RELIED_ON-ENTITIES -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / * OTHER-EO-NOT_RELIED_ON-ENTITIES -> Group #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d added at the end of the structure / The documentation has been changed accordingly: the images corresponding to all these data structures have been updated.	GROUP #UUID 9026e403-3eb6-4705-a9e9-e21a1efc867d IS NOW ASSOCIATED TO ALL CRITERIA WITH cardinality 1.
112	Schematron error when ESPD Response contains Lot Information	CLOSED	The schematron used for validation of ESPD Response 1.0.2 contains the following rule which is problematic: / <reports> / <error xsi:type="BAR"> / <description>The current version of the ESPD Service does not allow for the specification of multiple lots. To ensure conformace with the current version of the ESPD Service the ID sub-element inside the element ProcurementProjectLot MUST be 0 (zero).</description> / <location>xml:84:0</location> / <test>( not(cbc:ID!='0') )</test> / </error> / </reports> / However, the ESPD Response has a field specifically for defining lots which uses the specific UBL Element. / The Schematron should be updated to reflect the correct business rule for ESPD Response 1.0.2 / Artifact and report as a zip file	2.0.1	PASS TO MARIA ASAP / This is being corrected in the Version 2.0.1 REGULATED version. We can correct this also for version 1.0.2 but in order to not having to create a new version 1.0.3 or similar I propose to create a folder with bug-fixes for version 1.0.2 ("Previous-versions-fixed-bugs") inside the distribution package of version 2.0.1. / What do you think about my proposal?	EDM V1.0.2	After revewing this story and origins of this issue the conclusions are: / 1. ESPD-EDM-V1.0.2 *cannot* be used for procurement procedures divided in lots. / 2. ESPD-EDM-V2.0.0 is intended to move from the GROWTH's proprietary specification towards the UBL-2.2 specification. It was decided to have two "flavours" of XML implementations, both based on the same common set of UBL schemas: / - ESPD-EDM-2.0.0 REGULATED, with the objective of ensuring backwards compatibility with the previous ESPD-EDM-1.0.2. This ESPD-EDM-2.0.0 REGULATED cannot be used for procedures divided into Lots, otherwise the compatibility would be broken. / - ESPD-EDM-2.0.0 Self-contained, which is much more flexible and can be used for procedures divided into Lots, but is not compatible with the previous version 1.0.2. / **In conclusion: the Schematron rule is correct and should not be modified.**
111	C36 - Other economic or financial requirements	CLOSED	As per so many of the new criteria updates, there are grammar errors in the text. / "Concerning the other economic or financial requirements, if any, that may have been specified in the relevant notice or the in the ESPD, the relevant notice or , the economic operator declares that:" / Were the updates automated? There are grammar mistakes throughout.	2.0.1		EDM 2.0.1 Documentation	Definitions in the Data Structure spread-sheets containing syntax and grammar errors have been corrected. / This particular C36 error has been corrected in the documentation and will appear as so in version 2.0.1.
110	C23 - Multiple line description	CLOSED	Can you please explain what the following means: / "BEWARE THAT IN THIS CASE, THE CRITERION DESCRIPTION IS SPLIT IN THREE LINES. THIS WILL GENERATE THREE DESCRIPTION ELEMENTS IN THE XML INSTANCE (THE UBL-2.2 XSD SCHEMA DOES ALWAY CATTER FOR 0..n DESCRIPTION LINES." / In the example response you have provided this is not the case, in fact a/b/c is not included	2.0.1	The transformation XLST artefacts in version 2.0.0 and 2.0.1 are not coping with this. Try and modify the artefacts to fix this problem in version 2.0.3.	1. EDM 2.0.1 Documentation / 2. XML examples	The documentation and XML have been corrected/improved.
109	C7 - Payment of taxes	CLOSED	There seems to be a new subgroup with element code ONFALSE / The question is / "If this breach of obligations was established through a judicial or administrative decision, was this decision final and binding?" / This makes no sense if the answer to the original question was no	2.0.1			We have been reviewing the behaviour of the ESPD Service and, in principle, the ONFALSE code would be rightly used in the data structure defined in version 2.0.0. It is linked to the question: "Has this breach of obligations been established by means other than a judicial or administrative decision?" If the answer is "yes" (ONTRUE) the field "Please describe which means were used" is shown. / On the opposite, if the answer is "no" (ONFALSE) the question "If this breach of obligations was established through a judicial or administrative decision, was this decision final and binding?" is shown.
108	C30 - CPV codes	CLOSED	Question 30 asks for CPV codes, is that intentional?	2.0.1	MC: Yes this is intentional because it will allow the CA to either use a business domain description OR a CPV code to provide the domain for the yearly turnover. / Text will be checked.	1. Documentation	MC is right. Additional explanatory texts have been added at the beginning of sections "VI.2.6 Self-contained specific yearly turnover" and "VI.2.8 Self-contained specific average turnover", e.g.: / **One characteristic of the "specific" turnovers is that the contracting authority requires to know which is the economic operator's turnover for a concrete business domain. The only way of responding that requirement is either by describing the domain in a free-text field or to use the Common Procurement Vocabulary (CPV) codes to narrow as much as possible the business domain. / Notice that in the Mock-ups and the Data Structures, below, both options are available to the economic operator. / See also section about the SELF-CONTAINED specific average turnover.**
107	C22 - Incorrect Element Code	CLOSED	Have you taken measures to demonstrate your reliability (Self-Cleaning)? / This should be an indicator	2.0.1	MC: Yes, it is wrong, it should be an indicator. We will update the spec.	1. Data Structures / 2. Documentation	Many thanks for contributing to the quality of the specification, Millstream. This has been corrected in version 2.0.1. The following artefacts have been updated: / Criterion 22 in the REGULATED Data Structures spreadsheets book / Criterion 22 in the SELF-CONTAINED Data Structures spreadsheets book / The online documentation (released on the 25th February 2018 on the Github v2.0.1 branch)
106	C22 - Element Code Mistake	CLOSED	If initial answer is yes, please describe them subgroup should have process instruction ONTRUE	2.0.1	MC: We will update the spec.	1. Data Structures / 2. Documentation	Many thanks for contributing to the quality of the specification, Millstream. This has been corrected in version 2.0.1. The following artefacts have been updated: / Criterion 22 in the REGULATED Data Structures spreadsheets book / Criterion 22 in the SELF-CONTAINED Data Structures spreadsheets book / The online documentation (released on the 25th February 2018 on the Github v2.0.1 branch)
105	C20 - Spelling Mistake	CLOSED	Is the economic operator aware of any conflict of interest, as indicated in national law, the relevant notice or the in the ESPD, the relevant notice or due to its participation in the procurement procedure?	2.0.1	MC: We update the text	1. Data Structures / 2. Criteria Taxonomy spread-sheets (see dist/cl folder)	Corrected in v2.0.1 to be released on the Github 2.0.1 branch by the 25th February 2018: / 1. The REGULATED version now reads: Is the economic operator aware of any conflict of interest, as indicated in national law, the relevant notice or in the ESPD, the relevant notice or due to its participation in the procurement procedure? / 2. The SELF-CONTAINED version now reads: Is the economic operator aware of any conflict of interest, as indicated in the ESPD additionally to the national law or the relevant notice, the relevant notice or due to its participation in the procurement procedure?
104	C18 + C19 = Wrong element code	CLOSED	Have you taken measures to demonstrate your reliability / The subgroup it belongs to should have ONTRUE as its element code.	2.0.1	Correct, we will update the spec.	1. Data Structures / 2. Documentation	Corrected in v2.0.1 to be released on the Github 2.0.1 branch by the 25th February 2018.
103	C18 + Question Description	CLOSED	The grammar in this question makes no sense / Is the economic operator guilty of grave professional misconduct? Where applicable, see definitions in national law, the relevant notice or the in the ESPD, the relevant notice or .	2.0.1	MC: We will update the spec.	1. Data Structures / 2. Criteria Taxonomy spread-sheets (see dist/cl folder) / 2. Documentation	Corrected in v2.0.1 to be released on the Github 2.0.1 branch by the 25th February 2018 (both in the data structures and the Criteria Taxonomy spreadsheets, see "dist/cl" folder files). / The REGULATED version now reads: Is the economic operator guilty of grave professional misconduct? Where applicable, see definitions in national law, the relevant notice or the procurement documents. / The SELF-CONTAINED version now reads: Is the economic operator guilty of grave professional misconduct? Where applicable, see definitions in the ESPD and the national law, the relevant notice or the procurement documents.
102	Available Electronically Question	CLOSED	It appears that the question / Is this information available electronically? / has changed to / Is this information available at no cost to the authorities from an EU Member State database? / Can you please confirm if this was intentional?	2.0.1	MC: We will use "Is this information available electronically?". The information about / at no cost / for authorities / in an EU Member State database / will be provided in the future through eCertis. And it would be a problem if we would combine the requirements into the question. / We will update the specs.	1. Data Structures / 2. Documentation	The text "Is this information available at no cost to the authorities from an EU Member State database?" has been replaced by "Is this information available electronically?" in the data structure files (both REGULATED and SELF-CONTAINED) and in the online documentation. To be released in version 2.0.1 by the 25th February 2015 on Github branch 2.0.1.
101	Criteria 9-11	CLOSED	Mapping document indicates the following question should be of type DESCRIPTION, but it should be of type INDICATOR / Have you taken measures to demonstrate your reliability (Self-Cleaning)?	2.0.1	MC: We will update the spec	1. Data Structures / 2. Documentation	Corrected in v2.0.1 to be released on the Github 2.0.1 branch by the 25th February 2018.
98	Element Code	CLOSED	Can you please explain the logic behind ON* in the criteria data structure please? / Normally it is ONTRUE or ONFALSE	2.0.1	AM: ON* means "show always". We will include this clarification to the documentation in https://espd.github.io/ESPD-EDM/v2.0.0/xml_guide.html	1. Documentation	The ESPD-EDM 'criterion' entity is a very flexible and business-agnostic structure. This flexibility provides a convenient way to represent any type of criteria. The counterpart is that the semantics of the criteria needs to be delimited based on codes, identifiers and design rules. / Hence this document proposes a way of representing the criteria following a regular method and providing concrete codes to specify types of criterion properties, and identifiers to distinguish the different criteria and reusable groups of properties (when studying these data groups you will observe that sub-groups of properties are reused in different criteria have identical identifiers and structures). / The following two figures below illustrate the data structure sheets for one simple exclusion criterion (EG-Contributions) from both versions of the ESPD, REGULATED and SELF-CONTAINED. Compare them with the UBL-2.2 cac:TenderingCriterion XSD element. / The columns of the tables are to be interpreted as follows: / Column 1: an ordinal number to sort sequentially the criteria / Column 2: contains always the opening and closing tag for Criterion / Columns 3 to 17: reserved for the opening and closing tags defining the data structure (see the tag codes in code list CriterionElementType). / Column 18: Name, a short descriptive text to identify the criterion withouth having to read the description / Column 19: Description, the text describing the criterion as kept in e-Certis / Column 20: Value a possible value or description of the value used by the transformation artefacts to produce example XML instances / Column 21: Cardinality, indicates whether the element is mandatory or optional and its multiplicity / Column 22: PropertyDataType, the type of data expected according to the types defined in the code list ResponseDataType / Column 23: ElementUUID, The Universal Unique Identifier assigned to identify unambiguously a criterion, group or subgroup. These UUID are kept in e-Certis, except for those that have to be generated dynamically (e.g. UUIDs for Questions, Captions and Requirements). / Column 24: Element Code; in the case of Criterion it contains the code that categorises the criterion in the taxonomy of exclusion and selection criteria (it maps to the taxonomy drawn in the online documentation and in the spread-sheet files "ESPD-CriteriaTaxonomy*" in folder dist/cl). For the rest of elements there are three types of codes: / ON*, meaning "process always" (e.g. show always or read and extract data always") / ONTRUE, meaning "process only if the previous parent question (always an INDICATOR) has been answered affirmatively / ONFALSE, meaning "process only if the previous parent question (always an INDICATOR) has been answered negatively
97	All criteria satisfied	CLOSED	Can you please explain how 'all criteria satisfied' is handled in the new model as there does not appear to be a criteria? / CRITERION.SELECTION.ALL_SATISFIED	2.0.1	AM: This relates to the alpha criterion and was intenitally not foreseen in version 2.0.0 (regulated and self-contained). We will elaborate if and how it can be included to version 2.0.1. The current discussion has shown that we propably will include this alpha criterion for the "regulated" ESPD version 2.0.1 to maintain equivalence with version 1.0.2 and legal validity. However, in the "self-contained" ESPD version 2.0.1 the intention is still to deprecate this alpha criterion.	1. Data Structures / 2. Documentation	The decision is not to have it in version 2.0.1 as this breaks all possibility of interoperability. However you still have the possibility of "repealling" this decision and we could re-discuss if this should go or not to version 2.0.2.
96	CRITERIATYPE > CPV & LOTS	CLOSED	The list of Criteria type appears to be missing CPV, SME and LOTS, can you please confirm if these are still meant to be criteria? / C63 - LOTS / C64 - CPV / C66 - SME	2.0.1	AM: The max. Quantity of criteria is 64. In C63 the properties were missing and we corrected it. However, we do not found the exact part of the specification refering to C64 and C66. Could you please clarify which part of the specification you are refering to?	1. Data Structures / 2. Documentation	C62 and C63: Relied on entities three questions had no PropertyDataType assigned. / Corrected in v2.0.1 to be released by the 25th February 2018.
95	SELECTION > SUITABILITY Criteria	CLOSED	New implementation guide excludes suitability questions from the taxonomy tree, yet the criteria is listed in the taxonomy doc. Is this a mistake? / Similarly in the exclusion section there seems to be a new EARLY_TERMINATION sub section, however the taxonomy list does not represent this.	2.0.1	We will elaborate the issue in the documentation and correct the issue. It seems to be an editorial inconsistency.	1. Documentation	Indeed there were errors in the representation of both taxonomies: the one about the Exclusion Criteria and the one about the Exclusion Criteria. / The drawings in the documentation have been updated to match the Criteria Taxonomy category codes as they appear in the spread-sheet books "ESPD-CriteriaTaxonomy-" and "ESPD-Data_Structures-".
63	ESPD XML Schema version incosistencies	CLOSED	The ESPD XML Schema version, according to the document found at https://espd.github.io/ESPD-EDM/#root-properties states that the version must always be 2014.06.02 / Rule: Use always the value "2016.04.2 for this version (this may change in future releases) / but the current ESPD Service Version marks the Schema version as 2017.01.01. Why we are using deployment dates for the ESPD Schema versions? / Which is the correct version of the Schema? / What are the differences between 2016.04.02 and 2017.01.01? (change logs?) / Should we consider 2016.04.02 incompatible with 2017.01.01? / Shouldn't it be better if we just use 1.0.2 instead?	2.0.1	See proposal in Issue #82 "Possibility to refer an Xml Version in the Data Model".		From version 2.0.1 on the UBL-2.2 ProfileExecutionID will be used to specify the exact version of the ESPD-EDM. See values in the CodeList "ProfileExecutionID".